## Sheet1
Tasks and Assignment Breakdown
| Group: | group 4
| Team Members (and initials): | Fabian Caraballo (FC), Clark Chen (CC), Joseph Shea-Bianco (JSB), Creston Wilson (CW), Kaijing Zhang (KZ)
| Date this was last updated: | 2019-01-30
| Last updated by (whom): | CC
Grouping | Task or Milestone (with an objectively verifiable completion) | Status | Assigned to (whom) | Date Assigned | Date Due | Date Completed | Completed by (whom) | Confirmed Completed by (whom) | Date Confirmed Complete | Notes
Week 1
| Write V1 of project plan | completed | All staff | 2019-01-11 | 2019-01-16 | 2019-01-15 | All staff | CC | 2019-01-15
| Write V1 of software requirements specification | completed | All staff | 2019-01-11 | 2019-01-16 | 2019-01-15 | All staff | CC | 2019-01-15
| Write V1 of software design specification | completed | All staff | 2019-01-11 | 2019-01-16 | 2019-01-15 | All staff | CC | 2019-01-15
| Group meeting | completed | All staff | 2019-01-14 | 2019-01-14 | 2019-01-14 | All staff | CC | 2019-01-14
| Meet with Professor Hornof to review initial documentation | completed | All staff | 2019-01-16 | 2019-01-18 | 2019-01-18 | All staff | CC | 2019-01-18
| Group meeting | completed | All staff | 2019-01-19 | 2019-01-19 | 2019-01-19 | All staff | CC | 2019-01-19
Week 2
| Write V2 of project plan | completed | All staff | 2019-01-19 | 2019-01-21 | 2019-01-21 | All staff | CC | 2019-01-21
| Write V2 of software requirements specification | completed | All staff | 2019-01-19 | 2019-01-21 | 2019-01-21 | All staff | CC | 2019-01-21
| Group meeting | completed | FC/CC | 2019-01-19 | 2019-01-21 | 2019-01-21 | FC/CC | CC | 2019-01-21
| Write V2 of software design specification | completed | All staff | 2019-01-19 | 2019-01-21 | 2019-01-21 | All staff | CC | 2019-01-21
| Group meeting | completed | All staff | 2019-01-21 | 2019-01-26 | 2019-01-26 | All staff | CC | 2019-01-26
Week 3
| Group meeting | completed | All staff | 2019-01-26 | 2019-01-29 | 2019-01-29 | All staff | CC | 2019-01-29
| Group meeting | completed | All staff | 2019-01-26 | 2019-01-31 | 2019-01-31 | All staff | CC | 2019-01-31
| Implement database | completed | JSB | 2019-01-26 | 2019-01-27 | 2019-01-27 | JSB | CC | 2019-01-27
| Create Python functions | completed | KZ | 2019-01-26 | 2019-01-28 | 2019-01-28 | KZ | CC | 2019-01-28
| Finalize Python functions | completed | FC/CW | 2019-01-28 | 2019-01-30 | 2019-01-30 | FC/CW | CC | 2019-01-30
| Meet with Professor Hornof to review progress | complete | All staff | 2019-01-29 | 2019-02-01 |  |  | CC
Week 4
| Group meeting | complete | All staff | 2019-01-30 | 2019-02-02 | 2019-02-02 | All staff | CC | 2019-02-02
| Connect frontend to backend | complete | FC/JSB/KZ | 2019-01-30 | 2019-02-02 | 2019-02-02 | FC/JSB/KZ | CC | 2019-02-02
| Modify UI | complete | CW | 2019-01-30 | 2019-02-02 | 2019-02-02 | CW | CC | 2019-02-02
| Group Meeting | complete | All staff | 2019-01-30 | 2019-02-03 | 2019-02-03 | All staff | CC | 2019-02-03
| Testing | complete | FC/CC/JSB | 2019-01-30 | 2019-02-04 | 2019-02-04 | FC/CC/JSB | CC | 2019-02-04
| Write documentation | complete | CC | 2019-01-30 | 2019-02-04 | 2019-02-05 | All staff | CC | 2019-02-05 | Takes time to complete the docs